## Action Plan
HREiR Action Plan 2023-2026
| Institution name: | University of Lincoln |  |  |  | The institutional audience* for this action plan includes (only include direct beneficiaries; complete or delete, as appropriate):
| Cohort number: | 19 |  |  |  | Audience (direct beneficiaries of the action plan) |  | Number of | Comments
| Date of submission: | 2023-01-27 |  |  |  |  | Research staff | 114
| Institutional context: | At the University of Lincoln, all academics (up to Associate Professor) have the same contractual obligations. Within the academic contract, two role profile pathways exist: Teaching and Research (T&R), and Teaching, Scholarship and Professional Practice (TSPP). These role profiles allow an increased focus on specific areas of activity for individuals to ensure we achieve our strategic aims as a University. As of January 2023, there are currently 396 academics on the T&R profile and 579 academics on the TSPP profile. There are currently 114 employees on research only contracts at the University. Postgraduate researchers, employees on research only contracts and Early Career Researchers on both the T&R and TSPP profiles are the intended audience of ongoing engagement, consultation, development opportunities and the action plan for the Researcher Development Concordat. |  |  |  |  | Postgraduate researchers | 458 | As of 26 January 2023
[7 empty] | Research and teaching staff | 975 | Including academics on Teaching and Research (T&R) and Teaching, Scholarly and Professional Practice (TSPP) profiles
Complete for submission | [7 empty] | To be completed only when reporting on action plan
| Obligation | Action | Carried over from previous action plan? | Deadline | Responsibility | The targeted impact of the action (success measure) | Comments (optional) | Progress update | The actual impact of the action (reporting against the success measure) | Outcome (ongoing/carried forward/no further action)
Environment and Culture
Awareness and engagement
The aims of these obligations are to work towards an open and inclusive research culture, and to ensure broad understanding and awareness of this amongst researchers.
ECI1 | Ensure all relevant staff are aware of the Concordat. | a) Engage the Concordat consultation group at least three times per year, while reviewing and further developing the action plan. At the meetings have 'you said, we did' sections where the positive impact of the group (and resultant work) will be demonstrated. b) Launch new action plan and promote to all research staff with support from DVC for Research and Innovation. Ensure researchers are aware of the University's obligations with respect to the Concordat. c) Develop e-training module on the Researcher Development Concordat for all new researchers, to be promoted as part of new research induction, which is specifically aimed at research staff. | No | 2023-08-01 | a and b) People Change and Policy Manager, and Researcher Development Officer c) Researcher Development Officer | i) CEDARS 2021: 29.2% of respondents had some understanding of the Researcher Development Concordat. Increase this to 40% of researchers in CEDARS 2023. ii) Increase the overall response to CEDARS 2025 to 150 completions, with an increase in research only staff responses by 10%, and ECR responses by 10%. iii) Increase engagement in the Concordat Consultation Group from 45 members to 50 by the end of 2023, with the additional members being research staffeCRs. iv) Evaluate the impact of researcher initiatives through consultation and discussion with research networks, ECR forums/networks and the Concordat consultation group v) Ongoing improvement in awareness of the Concordat and HR Excellence in Research Award as measured by the responses of researchers to the annual colleague survey vi) Measure awareness of the Researcher Development Concordat through research staff induction feedback forms, 6 months post-event. Increase in responses in those who have awareness of the principles and responsibilities by 10% for each event. | a) It is hoped these actions will further increase members, as members will then be likely to encourage their fellow researchers to attend.
ECI2 | Ensure institutional policies and practices relevant to researchers are inclusive, equitable and transparent, and are well-communicated to researchers and their managers. | a) To understand why Black, Asian and minority ethnic (BAME) research staff report being encouraged to apply for promotion at a lower frequency rate than white staff and how this can be improved. b) Review the Academic Promotions and Role Transfer Processes to ensure they are inclusive and transparent and are intrinsically linked to management discussions, including appraisals. c) Conduct a review of the Academic Role Profiles. Consider a specific entry route for ECRs into the University, including possibly a different probation process with different levels of support in comparison to more established researchers. d) All new research policies and procedures to have an Equality Impact Assessment (EIA) completed prior to approval e) Create a dedicated information hub for research staff. This will pull together all the information research staff will need during their time at the University, including information about local support, PDRs, training and development opportunities and links to University-wide information, guidance documents and policies. | a) No b) Yes c-e) No | a-b) June 2023 c) Dec 2024 d) June 2023 e) Dec 2024 | a) Director of Inclusive Practice b) People Change and Policy Manager c) People Change and Policy Manager, Head of People Business Partnering and Head of Organisational Development d) Director of Inclusive Practice e) Researcher Development Officer | i) 77.1% of UoL respondents in CEDARS 2021 believed the institution is committed to equality and diversity (agree or strongly agree). Increase this figure to 85% in CEDARS 2025. ii) In CEDARS 2021, 57% of respondents felt that staff are treated fairly irrespecetive of protected characteristcs, increase this figure to 65% in CEDARS 2025. iii) There have been 64 successful academic promotions in the last five years (2016-2019). Ensure that there are case studies cascaded and research staff are aware of support available to continue to increase this number year on year, in particular for BAME and female academics. iv) Evaluate the impact of institutional policies and practices relevant to researchers through consultation and discussion with research networks and the Concordat consultation group
ECI6 | Regularly review and report on the quality of the research environment and culture, including seeking feedback from researchers, and using the outcomes to improve institutional practices. | a) Run CEDARS in 2023 and 2025 to seek feedback from researchers to help implement change. Encourage participation from research staff in particular through promotion cascading down from SLT to HoSs and managers of researchers. b) Run PRES in spring 2023. c) Research environment and development (including results from CEDARS surveys and related actions plan) to be discussed at the Research and Knowledge Exchange Committee agenda, with a focus on feedback from research staff. | No | 2025-08-01 | a) Research Development Officer and People Change and Policy Manager b) Director of Doctoral School c) Head of Research and Industrial Partnerships | See ECI1 plus: i) Increase PGR participation in the PRES from 19% (2022) to 25% in 2023.
ECR1 | Encourage researchers to actively contribute to the development and maintenance of a supportive, fair and inclusive research culture and be a supportive colleague, particularly to newer researchers and students. | a) Develop the Researcher Induction session to ensure EDI principles are embedded, and to promote and ensure understanding of researcher responsibilities as part of the Concordat. b) Doctoral School to work with Postgraduate Leads to develop resources to further promote good supervision practice. This will help to ensure rsearchers are appropriately supported and are made aware of their responsibilities within a fair and inclusive research culture. c) Appoint a student representative as a member of the Doctoral Management Board. d) Pilot a researcher buddy scheme for new research staff at a local level (this would be optional for those who wish to participate), as well as continuing to promote more formal mentoring routes, e.g. Pipeline Inclusive Mentoring Scheme | a, b) No c) Yes d) No | 2023-12-01 | a) Researcher Development Officer b, c) Director of Doctoral School d) Researcher Development Officer | i) 94% of staff engaged with Stress Awareness training in 2022, ensure this does not fall below 90% engagement by 2025. ii) 90% of staff engaged with Equality and Diversity training in 2022, ensure this does not fall below 90% engagement by 2025. iii) 68% of staff engaged with the new Safeguarding training following its launch in July 2020, increase this to over 75% by 2024. iv) In CEDARS 2021, 57% of respondents felt that staff are treated fairly irrespecetive of protected characteristcs, increase this figure to 65% in CEDARS 2025. v) Evaluate the impact of initiatives to create a supportive, fair and inclusive research culture through consultation and discussion with research networks and the Concordat consultation group vi) Increase the engagement of research staff with the Pipeline Inclusive Mentoring scheme by 5% in 2023/24. | i and ii) We have set lower completion rate targets for 2025 due to turnover rates being very high in 2022, which is having a significant impact on mandatory training completion rates. Also because refresher training will be delivered to all staff in 2023, which will reduce the completion rates down to 0%.
Wellbeing and mental health
The aims of these obligations are to champion positive wellbeing amongst researchers, both through appropriate training and enabling new ways of working.
ECI3 | Promote good mental health and wellbeing through the effective management of workloads and people. | a) Review of the Workloading aspect of AAPR in 2023 in consultation with researchers at all levels, which will provide clarity on workload and better understanding where there are strains in work-life balance. b) Use evidence-based priniciples developed by Jackman et al. to further develop a long, thin Doctoral School induction to support researchers mental health and wellbeing. c) Doctoral School to provide guidance on supporting mental health and wellbeing of students via supervisor training and other online resources. | a) Yes b, c, d) No | 2023-09-01 | a) People Change and Policy Manager b, c) Director of Doctoral School and Research Development Officer | i) Report on the improvements implemented and supported by the Wellbeing strategy, and evaluate efficacy of the strategy through ECR forums and networks. To continue to report on and monitor mental health absence figures. ii) 55.2% of UoL respondents to CEDARS 2021 felt that the insitution actively promotes the importance of mental health and wellbeing amongst staff. Increase this figure to 65% in CEDARS 2025. iii) In PRES 2023, increase the percentage of PGRs who agree that "The support for my health and wellbeing meets my needs" from 60.2% to 65%. iv) UoL Staff Survey 2022; "I know how to access mental health and wellbeing support at the University", the average score for all staff was 5.6 (on a scale of 1-7, with 1 representing Strongly Disagree and 7 representing Strongly Agree), the average score for research staff was slightly lower at 5.5. To measure success by increasing the average score for research staff to 6 in UoL Staff Survey 2024.
ECI4 | Ensure managers of researchers are effectively trained in relation to wellbeing and mental health. | a) Embed wellbeing and mental health support strategies for research supervisors within their supervisor training. b) Promote guidance encouraging regular 121s that discuss wellbeing and mental health e.g. HR Line and New Ways of Working. c) Mandatory refresher training to be introduced for all core staff, including managers of researchers, from January 2023. Heads of Area to receive monthly reports on completion rates and completion rates will be reported in high level to SLT on a quarterly basis. d) Mental Health First Aider refresher training programmes will be targeted towards both managers of researchers and research supervisors. | a) No b) Yes c) No | 2023-09-01 | a) Director of Doctoral School b) Head of Organisational Development and Employee Wellbeing and Engagement Manager c) Head of Organisational Development d) Head of Organisational Development and Employee Wellbeing and Engagement | i) 94% of staff engaged with Stress Awareness training in 2022, ensure this does not fall below 90% engagement by 2025. ii) 68% of staff completed Safeguarding training in 2022. Maintain this completion rate for 2023. iii) Increase the number of managers of researchers who have completed Stress Awareness and Safeguarding training from 35.2% in 2022 to 45% in 2025. iv) Ascertain and assess levels of confidence of managers/supervisors in supporting mental health and wellbeing through course feedback. | i) We have set a lower completion rate target for 2025 due to turnover rates being very high in 2022, which is having a significant impact on mandatory training completion rates. Also because refresher training will be delivered to all staff in 2023, which will reduce the completion rate down to 0%. ii) The University will be asking all core staff in 2023 to attend a new updated face to face session, which will take the University back down to 0% completion rates as the online course will only work as a refresher module after 2 years. As such a realistic success measure will be to achieve a 68% completion in 2023.
ECM3 | Ensure managers promote a healthy working environment that supports researchers' wellbeing and mental health. | a) Managers of researchers will be encouraged to "Promote and Support the health and wellbeing of our people" as part of the People and Cutlure sub-strategy of the University's Strategic Plan 2022-27, and will be provided with regular updates and information to ensure that they are aware of the support available. b) Influence and enable managers of researchers to apply the principles of the Mental Health Charter to encourage change, to strengthen the overall health and wellbeing support available to all colleagues, including researchers. This will be carried out through targeted dissemination of the University's Mental Health Charter action plan. | No | 2023-12-01 | a) Heads of School and People Change and Policy Manager b) Deputy Director of PPC and Employee Wellbeing & Engagement Manager | See ECI3 plus: i) Aim for a percentage of respondents who agree that their working environment supports mental health and wellbeing from 34.6% (CEDARS 2021) to 45% in CEDARS 2023. ii) In October 2022 there were 120 trained Mental Health First Aiders. Ensure this figure is maintained at an amount which equates to at least 5% of the core workforce in 2025. Increase the percentage of Mental Health First Aiders who are researchers. | ii) 5% of the core workforce who are trained to provide assistance during a mental health crisis is deemed by the institution to be suitable and sustainable.
ECM4 | Ensure managers consider fully flexible working requests and other appropriate arrangements to support researchers. | a) The EGI to develop a case for a non-STEMM version of the Academic Returners Research Fund. b) Embed the University Hybrid Working Guidance to enable flexible and agile colleagues to deliver in a fast-paced environment. c) Update the Flexible Working Policy in advance of the Government's intended changes to flexible working legislation, to help staff balance their personal lives with their working lives. PPC to raise awareness to managers of researchers through appropriate communication channels and ensure managers and individuals are supported when a flexible working request is submitted. | a) No | a) March 2024 b) September 2023 c) March 2023 | a) Director of Inclusive Practice b) Head of People Business Partnering | i) In CEDARS 2023, increase the percentage of respondents who believe the institution treats them fairly in relation to flexible working requests from 61% (2021) to 65%. ii) In REC 2021 66.7% of BAME staff and 73.4% of White staff are aware of the flexible working policies; a measure of success would be to increase this to 80% for all staff in REC 2025. iii) In REC 2021 45.5% of BAME staff and 69.7% of White staff were confident a request for flexible working would be granted if feasible; a measure of success would be to increase this to 70% for all staff in REC 2025. iv) Evaluate the flexible working support available to researchers through consultation and discussion with research networks and the Concordat consultation group. | a) The purpose of the Academic Returners’ Research Fund is to provide the opportunity for female scientists to plan how their research commitments and aspirations can be supported during and/or after maternity leave and to enable them to continue their research endeavours in and around this period. For each period of maternity leave, each applicant is entitled to apply for up to £10,000 of funding. c) Flexible working will become a day one right, managers to consult with staff if they intend to reject a flexible working request and staff will be allowed to make two statutory requests in any 12 month period (rather than the current one).
ECR3 | Ensure researchers take positive action towards maintaining their wellbeing and mental health. | a) Doctoral School Wellbeing/Mental Health awareness week aimed at PGRs and ECRs to take place in May 2023. b) Reguarly review themes identified through staff surveys and take appropriate action to support the health and wellbeing of our researcher community e.g. offer tailored support for researchers with respect to managing their financial stress and wellbeing as a result of the cost of living crisis. c) Run new initiatives designed to support the wellbeing of all staff, including researchers, such as inspirational talks about health and wellbeing from key figures, commencing the provision of on-site health-checks for staff, participation in the BRIT Challenge, introducing wellbeing rooms with guidance and resources on health and wellbeing issues, and opening a swimming pool on campus to support health and wellbeing. | No | 2023-05-01 | a) Researcher Development Officer b,c) Employee Wellbeing and Engagement Manager | i) 94% of staff engaged with Stress Awareness training in 2022, ensure this does not fall below 90% engagement by 2025. This is due to turnover rates being very high in 2022 which is having a significant impact on mandatory training completion rates and because refresher training will be delivered to everyone which will reduce the completion rates down to 0%. ii) Increase the number of respondents to CEDARS 2023 who agree that they take positive action to maintain their mental health and wellbeing from 76% (CEDARS 2021) to 80%. iii) Target of 30 PGRs and ECRs to engage in Doctoral School Mental Health Week 2023. iv) Researcher participation in the BRIT Challenge championed through research newsletters - at least two case studies per year to be shared with the wider research community. | c) The BRIT Challenge focuses on improving the mental and physical wellbeing of staff in universities and colleges across the UK.
Bullying and harassment
The aims of these obligations are to eliminate bullying and harassment in the research system, tackled through progressive policies and secure mechanisms to address incidents.
ECI3 | Promote a healthy working environment through effective policies and practice for tackling discrimination, bullying and harassment, including providing appropriate support for those reporting issues. | a) Launch and promote the new Bullying and Harrassment Policy in early 2023, in consultation with unions and other key stakeholders. b) Update and refresh the Active Bystander training | No | 2023-06-01 | a,b) People Change and Policy Manager | i) CEDARS 2021: 70.6% of UoL respondents felt confident that they could respond to issues relating to bullying and harrassment, and 67% were familiar with the institutions mechanisms to report bullying and harrassment. Aim for scores of 75% in both categories in CEDARS 2025. ii) Staff Survey, 2022: "If I raised a concern about discrimination, I am confident the University would do what is right"; the average score for all staff was 5.2, the average score for research staff was 5.3 (scale of 1-7 with 1 representing Strongly Disagree and 7 representing Strongly Agree). In light of the new Bullying and Harassment Policy and the associated communication and training that will take place around it's launch in early 2023, a measure of success will be improving this average score to 5.9 in the Staff Survey 2025. iii) Gain feedback from research-only staff and ECRs though discussion at the CCG, ECR forums, and research networks to assess the efficacy of the new Bullying and Harrassment Policy, and the updated Active Bystander training. | a) The new Bullying and Harassment policy will contain improved guidance with respect to what is and is not unacceptable behaviour, and how to report it. Going forward those employees who observe bullying and harassment will also be able to report it under the provision of the new policy. The new policy will have additional sections detailing the support available for staff both raising concerns about discrimination, bullying and harassment, and for staff who are responding to such complaints. The new policy will provide further detail regarding how the outcomes of investigations should be clearly communicated.
ECM3 | Ensure managers encourage reporting and addressing incidents of discrimination, bullying and harassment. | a) Promote the University's anonymous reporting system (Concern Line) following its relaunch in early 2023 and ensure that managers of researchers understand the purpose and process of the system that has been developed. b) Ensure managers of researchers are aware of the processes for reporting of discrimination, bullying and harassment via the new Bullying and Harassment policy training sessions, planned for 2023. | a) Yes b) No | 2023-07-01 | a) Director of Inclusive Practice b) People Change and Policy Manager, and Head of Organisational Development | i) Only 1 member of staff used Concern Line in 2022. See an increase in this number year on year. ii) PPC to record and produce annual reports on the numbers of researchers who report bullying and harrassment. Expect a reduction in the number of bullying and harassment complaints raised by researchers on an annual basis.
ECR4 | Ensure researchers use available mechanisms to report staff who fail to meet the expected standards of behaviour in relation to discrimination, harassment and bullying. | See ECI3
Equality, diversity and inclusion
The aims of these obligations are to ensure managers and researchers are trained in-, aware of- and adopt practices enhancing equality, diversity and inclusion.
ECI4 / ECM1 | Ensure managers undertake relevant training and development opportunities related to equality, diversity and inclusion, and put this into practice in their work. | a) To promote and report on managers of researchers' completion rates for Inclusive Leadership training, following a redesign of the course in 2023. b) In line with our Strategic Plan 2022-27, develop clear and transparent inclusive practice and processes, supported and measured through our Equality Charter Action Plans. c) In line with our Strategic Plan 2022-27, regularly review themes related to diversity and inclusion identified through our staff surveys and encourage localised departmental discussions on the themes to create action plans to address required change. d) Equality impact assessments will be conducted on research actions and support schemes. This will pull together an overall assessment of research and knowledge exchange funding, activity and achievements against EDI criteria, which will be reported through RKEC annually for monitoring and improvement action. | No | 2024-01-01 | a) Head of Organisational Development b, c) Director of Inclusive Practice d) EGI Director of Research | i) 66.7% of BAME respondents agree that ethnic/racial diversity of the HEI impacted their sense of belonging in comparison to 37.9% of White respondents (REC 2018). To increase awareness of the importance of diversity to researchers through inclusivity training, decolonising the curriculum and other EDI initiatives. ii) Completion rates for Inclusive Leadership training to be at least 95% in 2023.
ECR2 | Ensure researchers act in accordance with employer and funder policies related to equality, diversity and inclusion. | a) Promote the link between the Concordat and four new University of Lincoln equality projects comprising of Race, Gender, LGBTQ+, and Disability to researchers via internal communications mechanisms. | No | 2024-01-01 | a) Director of Inclusive Practice | i) Researchers encouraged to consider and embed inclusive practice when planning/carrying out research projects. Researchers will be approached and encouraged to provide examples of where they have applied these practices to be shared with the wider community.
Research Integrity
The aims of these obligations are to ensure managers and researchers are trained in-, aware of- and maintain high standards of research integrity, and are able to report infringements or misconduct.
ECI5 / ECM2 | Ensure researchers and their managers are aware of, and act in accordance with, the highest standards of research integrity and professional conduct. | a) Research Integrity training to take place during mandatory Doctoral School induction. b) Research Integrity training to promoted via the new research staff induction. Targeted approach to be taken to ensure all relevant colleagues receive this training. c) Update the Responsible Metrics Policy, which is based on the the San Francisco Declaration on Research Assessment (DORA) principles. | a, c) No b) Yes | 2024-08-01 | a) Research Governance Manager and Researcher Development Officer b) Research Governance Manager and Head of Organisational Development c) Head of RIPT and Research Repository and Research Data Officer | i) Increase the number of researchers who are aware of the Research Integrity Concordat. Aim for 30% of respondents in CEDARS 2023 who have some understanding of this. ii) Increase the number of managers of researchers who have completed research integrity training. Aim for 70% of respondents who have done this. For those who do not have formal responsibility for managing researchers, increase this figure from 40% (2021) to 50% in CEDARS 2025. iii) Internal monitoring of research-only staff who have undertaken research integrity training and consider targeted promotion through Schools/Colleges tp ensure high levels of understanding. If appropriate, bespoke training to be provided to ECRs forums/networks. iv) Increase the percentage of students agreeing that "My understanding of 'research integrity' (e.g. rigour, ethics, transparency, attributing the contribution of others) has developed during my programme" in PRES in 2023 to 90%.
ECM3 | Ensure managers report and address incidents of poor research integrity. | a) Produce e-training module on ethics for supervisors. b) University sharepoint pages to be updated regularly with the latest university guidance informed by UKRIO, for example, the Procedure for the Investigation for Misconduct in Research. | No | 2023-12-01 | a and b) Research Governance Manager | i) Ensure that all staff are aware of the institution's mechanisms to report research misconduct. Increase percentage of respondents who agree with this statement from 66% in CEDARS 2021 to 70% in CEDARS 2023, as well as anticpate an increase in enquiries to Named Person under the UKRIO procedure. ii) Increase the number of staff who feel they trust UoL to investigate reported incidents of misconduct from 64% in CEDARS 2021 to 70% in CEDARS 2025.
ECR2 | Ensure researchers act in accordance with employer and funder policies related to research integrity. | As per ECI5/ECM2
ECR4 | Ensure researchers use available mechanisms to report staff who fail to meet the expected standards of behaviour in relation to research misconduct. | a) Include information on reporting mechanisms in new research staff induction, and encourage open dialogue on research integrity. | No | 2023-12-01 | a) Research Governance Manager | i) See an increase in research-only staff engagement with materials provided through induction, and receive views and feedback via induction course discussions. Monitor efficacy of training materials through increased reporting.
Policy development
The aims of these obligations are to encourage all researchers to actively contribute to the development of policies driving positive change at their institution.
EI7 | Consider researchers and their managers as key stakeholders within the institution and provide them with formal opportunities to engage with relevant organisational policy and decision-making. | a) Encourage researcher engagement with the Lincoln Policy Hub. b) Managers of researchers to attend management engagement forums that are run by PPC for all managers and provide an opportunity to feedback on policies and processes, as well as engage as a group to learn from each other. | No | 2023-07-01 | a) Director of the Lincoln Policy Hub b) Head of Organisational Development | i) In CEDARS 2021, 28% of respondents felt valued for their contributions towards institutional policy and decision making (fully/mostly). Increase this figure to 35% by CEDARS 2025. ii) Increase PGR engagement with the concordat consultation group which contributes towards the design and implementation of the Concordat action plan. Aim for at least 5 PGR members by June 2023. iii) Increase ECR and research-only membership of the academic consultation group to 15 members by June 2024 to ensure fair and balanced views are taken into consideration when assessing progress against the Researcher Development Concordat action plan as well as other univeristy initiatives/policies. iv) Increase the number of respondents to CEDARS 2023 to 120, and 150 in 2025. v) In response to whether staff felt that the instution treated them fairly with regards to participating in decision-making processes (e.g. committees), 56% of respondents agreed in CEDARS 2021. Increase this figure to 60% in CEDARS 2025. vi) At least three case studies to be shared via the Lincoln Policy Hub blog promoting the research and achievements of research staff.
ECM5 | Encourage managers to engage with opportunities to contribute to policy development aimed at creating a more positive research environment and culture within their institution. | See EI7
EM5 | Engage with opportunities to contribute to relevant policy development within their institution. | See EI7
ECR5 | Encourage researchers to consider opportunities to contribute to policy development aimed at creating a more positive research environment and culture within their institution. | a) Aim to have an SU PGR officer a member of the Doctoral Management Board by June 2023. b) Encourage further responses in CEDARS 2023 from those who identify as an ECR. c) Encourage all research committes to ensure that researchers at all levels are fairly represented at meetings and encouraged to take part in discussion. | No | a) August 2023 b) June 2023 c) December 2024 | a) Director of Doctoral School b) Researcher Development Officer and People Change and Policy Manager c) Head of Research and Industrial Partnerships | i) In CEDARS 2021, 78% of respondents (with no formal line manager responsibilities) were interested in particpating in institutional policy and decision-making. Only 6% of respondents (2 researchers) had done this; in CEDARS 2025, increase this figure to 20%. ii) Increase the number of self-identifying ECRs responding to CEDARS from 8.5% of respondents in 2021 to 20% of respondents in 2025. iii) At least 80% of research committees across the university to have all levels of researcher representation through membership by December 2024.
ER4 | Recognise and act on their role as key stakeholders within their institution and the wider academic community. | a) Encourage engagement through promotion of the Research and Knowledge Exchange strategy within the Univeristy of Lincoln Strategic Plan 2022-27. This strategy aims to establish an international reputation for challenge-led, co-created, impactful research and knowledge exchange that addresses global and regional priorities. It is structured around three priority areas: Growth, Culture, and Collaboration. b) Work with college ECR networks in order to identify and provide opportunities for training and development activities, e.g research impact. | No | 2023-08-01 | a) Dean of Research Environment b) CDoRs | i) Align department strategies to the new Research and Knowledge exchange strategy, including the Doctoral School and LIAS. ii) In CEDARS 2021, 13.2% of respondents with no line management responsibility had taken part in public policy development. Increase this figure to 25% in CEDARS 2025. iii) Through ECR networks and forums, obtain feedback, through discussion, on training and development needs.
Employment
Recruitment and induction
The aims of these obligations are to ensure recruitment of researchers is open and fair and researchers receive effective inductions into the organisation.
EI1 | Ensure open, transparent and merit-based recruitment, which attracts excellent researchers, using fair and inclusive selection and appointment practices. | a) Understand the concerns raised by BAME research staff regarding transparency and fairness of the recruitment process in practice. EDI Culture Survey planned for February 2023 will help to provide an understanding of the concerns raised by BAME applicants. b) Support global mobility by encouraging and supporting overseas researchers to work at UoL, allowing for research exchange to be permeable by removing barriers to interaction between people across the world. This will be achieved by making improvements to the relocation policy which are planned to make the visa loan scheme more transparent, offering support with renting when staff from overseas initially come to the UK and providing support for visa costs by funding the first visa application of overseas staff. The number of right to work clinics offered by the University to new starters will also be increased. | Yes | 2023-04-01 | a) Director of Inclusive Practice and People Operational Services Manager b) People Officer (Visa and Immigration) and People Operational Services Manager | i) In CEDARS 2021, 90.5% of respondents recruited within the previous two years felt that their recrutiment appointment and selection process was fair; 87.5% agreed that it was inclusive; 81% agreed that it was transparent; and 85.7% agreed that it was merit-based. These are high results, so a measure of success would be to maintain (or improve upon) these results across all 4 measures in CEDARS 2025. ii) 30 people attended recruitment and selection training in 2021, increase attendance to at least 40 in 2024. iii) Only 3.3% of BAME applicants were offered a research position, in comparison to 20.5% of white applicants in 2021/22; this is the lowest offer rate for BAME staff for research vacancies over the last 6 years. Increase the offer rate of BAME staff for research vacancies to 9% by 2025. iv) Recruitment data for researchers will be monitored for any potential bias.
EI2 | Provide an effective induction, ensuring that researchers are integrated into the community and are aware of policies and practices relevant to their position. | a) Further development of research staff induction following Concordat consultation group discussons. Develop an induction that is long/thin to avoid overload of information at the start and through a variety of mediums. b) Schools/Colleges to set up ‘new starter talks’ where the new researchers can introduce themselves and their research to their schools. This can also be developed into a forum or platform to enable this. c) Provide additional information and support around the research environment, e.g. who to approach for support on bid writing, training on research impact for REF, and where to go for support regarding grant applications, via Research induction. Include online resources and handbook for future reference. Include new starter meeings with College/School Directors of Research on induction checklist. d) Use evidence-based priniciples developed by Jackman et al. to further develop a long, thin Doctoral School induction to support researchers mental health and wellbeing. e) Reference research inductions in new starter contracts/covering letters. f) Ensure the assignment of duties are appropriate for new research staff, establishing clear expectations and providing pump-priming support. | a-d) No e) Yes f) No | 2025-01-01 | a) Researcher Development Officer b) CDoRs c,d) Researcher Development Officer e) People Operational Services Manager f) College Directors of Research | i) Measure efficacy of staff induction via CEDARS 2025 for those who started within the previous two years by: an increase in those finding induction useful at institution and department level to 80% (which would be an increase compared to the CEDARS 2021 result of 71.4%). ii) Annual monitoring of research-only staff who attend research induction, and sharing findings with Heads of School/CDoRs. Increase attendance by 10% year-on-year.
Recognition, reward and promotion
The aims of these obligations are to ensure the fair and inclusive recognition of researchers as part of their career progression.
EI3 | Provide clear and transparent merit-based recognition, reward and promotion pathways that recognise the full range of researchers' contributions and the diversity of personal circumstances. | a) Continually review the benefits offering which include transparent reward mechanisms and promotion opportunities, with particular attention being given to BAME staff who feel that pay awards and increases are not allocated fairly. b) Demonstrate clear mechanisms for reward and recognition by developing a reward framework to support researchers. c) Identify clear career pathways for researchers, to aid their career development opportunities, thus developing, retaining and maximising the potential of researchers across the institution. Promote the use of the Vitae Researcher Development Framework/Planner in assisting with individual career development plans. d) Review the approach to specifying and evaluating knowledge exchange deliverables in role expectations, recruitment, support and promotion pathways, ensuring that there is parity of value with research deliverables. | a) Yes b-d) No | 2024-12-01 | a) Deputy Director of PPC and Director of Inclusive Practice b) Deputy Director of PPC c) Head of Organisational Development d) Head of Employability, Enterprise and Professional Practice | i) Evidenced in CEDARS 2025, in response to "my institution treats me fairly in relation to opportunities for promotion and progression", increase respondents who agree from 37% (CEDARS 2021) to 45% in CEDARS 2025. ii) REC 2021: 21.2% of BAME respondents agree that pay awards and increases are allocated fairly and transparently in comparison to 44.3% of White respondents. Increase BAME response to 35% to improve equity in REC 2023. iii) REC 2021: 9.1% of BAME academic respondents reported that they had been encouraged to apply for promotion in comparison to 15.2% of White academic respondents. Increase BAME response to 15% to improve equity in REC 2023. iv) Use the above surveys to identify and respond to issues/opportunities and feed back to the Concordat Consultation Group for discussion and implementation of future actions.
EM3 | Managers commit to, and evidence, the inclusive, equitable and transparent recruitment, promotion and reward of researchers. | a) Encourage promotion of researchers achievements at school and college level, e.g. awards for research and consultancy celebrated via instututional newsletters and staff news. b) Encourage participation of award winning (e.g. Docoral School grants) to share their success via events such as the PGR showcase. | a) Yes b, c) No | 2023-08-01 | a) CDoRs b) Researcher Development Officer | i) CEDARS 2021: 93% of managers were fully confident or confident ability to use inclusive, equitable and transparent recruitment processes. Increase to 95% in CEDARS 2025.
Responsibilities and reporting
The aims of these obligations are to ensure that researchers and their managers understand and act on their obligations and responsibilities.
EM2 | Managers familiarise themselves, and work in accordance with, relevant employment legislation and codes of practice, institutional policies, and the terms and conditions of grant funding. | a) Cascade Research Integrity information to colleagues by the research ethics leads / ethics leads form / module leads (for student research). b) Managers to attend new mandatory online supervisor ethics training. c) Ensure that any relevant legislation, codes of practice and institutional policies are published in easily accessible areas, and managers encouraged to lead on dicussions in these areas. | a, b) Yes c) No | 2023-12-01 | a) CDoRs b) Research Governance Manager c) People Change and Policy Manager and Researcher Development Officer | i) 50% of supervisors to have taken supervior ethics training in 23/24 academic year. ii) PPC, R&E and Secretariat teams to work collaboratively in producing a quartlerly bulletin aimed at managers of researchers with updates on new policies, procedures etc. Produce on Adobe Spark to allow assessment of readership. Aim to increase readership yearly by 10%. Assess researcher/ECR awareness of resources through an institutional survey on how useful they found it.
ER1 | Researchers ensure that they work in accordance with, institutional policies, procedures and employment legislation, as well as the requirements of their funder. | a) Encourage all new researchers to attend a newly developed research induction, which includes online resources and handbook. b) Staff to complete ethics and research integrity training as part of the Academic Development Programme. c) All staff undertaking research to read and understand the Code of Practice for Research and Research Ethics policy (signed declaration in online ethics system). The University publishes expectations in relation to Research Misconduct on its external and internal webpages and it is the responsibility of researchers to maintain current knowledge. | No | 2025-07-01 | a, b) Researcher Development Officer c) Research Governance Manager | i) Aim for 70% of PGRs to attend Doctoral School induction within first year of enrolment. ii) To achieve a 90% of research staff attendance to mandatory training on research integrity in the first year the course is available. iii) CEDARS 2021: 66% of respondents would feel comfortable reporting an incident of research misconduct, and 64.5% agreed that the institution would investigate incidents fairly. A measure of success will be to increase both of these results to 70% by CEDARS 2025.
ER2 | Researchers understand their reporting obligations and responsibilities. | As per ER1 |  |  |  | As per ER1
People management
The aims of these obligations are to ensure that researchers are well-managed and have effective and timely performance reviews.
EI4 | Provide effective line and project management training opportunities for managers of researchers, heads of department and equivalent. | a) Continue to develop training and guidance on specific research leadership and management. LIAS will provide a Research Leadership training programme to take place in early 2023. b) The Doctoral School to support up to 26 supervisors applying to the UKCE Research Supervisor Recognition Programme in 2023. | a) Yes b) No | 2024-07-01 | a) Dean of Research Environment b) Director of the Doctoral School | i) Research Leadership training to take place in March 2023. Aim for 16 attendees. ii) Encourage a minimum of 20 supervisors to apply successfully and gain recognition under the UKCGE Research Supervisor Recognition Programme in 2023.
EI5 | Ensure that excellent people management is championed throughout the organisation and embedded in institutional culture, through annual appraisals, transparent promotion criteria, and workload allocation. | a) Further develop our appraisal conversations to empower, support and enable our researchers to be ambitious and successful through clear objective setting and career planning. b) Conversations will take place with areas that had low researcher engagement with appraisals in academic year 2022/23 and action plans will be formulated to resolve any challenges. People Business Partners to work collaboratively with Heads of Area/School to ensure maximum engagement and completion. | No | 2024-12-01 | a) Head of Organisational Development b) Head of Organisational Development and Head of People Business Partnering | i) AAPR completion rates for 2022/23 were 84% across the University, however researchers only had a 58% completion rate. Aim for researchers to have an AAPR completion rate of 68% in 24/25. ii) In CEDARS 2021, 48% of respondents found appraisal to be useful. Increase this figure to 60% by CEDARS 2025. iii) In CEDARS 2021, 84% of managers of researchers were confident in their abilities to manage appraisals effectively. Aim to improve this score to 85% CEDARS 2025.
EM1 | Managers undertake relevant training and development opportunities so that they can manage researchers effectively and fulfil their duty of care. | See EI4
EM4 | Managers actively engage in regular constructive performance management with their researchers. | a) Review of Improving Performance Policy to take place in 2023, which will result in updated training regarding how to effectively manage performance. b) Encourage channels of communication between managers and their staff to enable maximum engagement and highlight barriers to efficiencies and performance. | No | 2023-12-01 | a) People Change and Policy Manager b) Heads of School | See EI5 and i) Explore improving performance as a topic of discussion at the Concordat Consultation Group and research network meetings to evaluate the impact of the new policy and seek feedback regarding what additional support may be required for research staff.
ER3 | Researchers positively engage with performance management discussions and reviews with their managers. | a) PGR students to attend mandatory Doctoral School induction which now includes a session on "Managing your supervisor" and includes expectations from both sides of the relationship. | No | 2023-12-01 | a) Director of the Doctoral School b) People Change and Policy Manager, and Researcher Development Officer | i) In CEDARS 2021, 48% of respondents found appraisal to be useful. Increase this figure to 60% by CEDARS 2025. ii) Explore appraisal as a topic of discussion at research network meetings to evaluate the impact of new policies. Feed back researcher views to colleagues in PPC along with Heads of Schools.
Job security
The aim of this obligation is to improve the job security of researchers.
EI6 | Seek to improve job security for researchers, for example through more effective redeployment processes and greater use of open-ended contracts, and report on progress. | a) Internal fund competition to be made available for bridging support for key researchers in between grants. b) Promote and embed the short-term research cover process, which was implemented in Spring 2021. c) Work with the sector to ensure best practice is shared with respect to providing support for researchers to find jobs and secure a career path (including considering options beyond academia). Gauge experiences with UoL engagement groups to determine what is required to support these plans or assist in career diversification | No | 2023-08-01 | a) Head of Research and Industrial Partnerships b) People Change and Policy Manager c) People Change and Policy Manager and Researcher Development Officer | i) CEDARS 2021: 32% had regular formal career development reviews. Increase this to 50% by CEDARS 2025. ii) CEDARS 2021: 68% of respondents said time to develop their research identity was not available to them. A measure of success will be to reduce this to 55% by CEDARS 2025. | b) There may be situations where cover is required to bridge a gap of employment contracts for externally funded projects, due to a resignation of an employee on a research only fixed term contract. A short-term research only vacancy cover process has been created to attempt to cover these gaps where there is either not enough time left before the end date of a project for external recruitment or cover is required while external recruitment is ongoing. This process encourages internal promotion and development, while providing opportunities for researchers to develop their career pathways and provide opportunities for cross-disciplinary working and development of transferable skills.
Professional and Career Development
Championing professional development
The aims of these obligations are to promote the importance of professional development and ensure researchers have the time to engage in it.
PCDI1 | Provide opportunities, structured support, encouragement and time for researchers to engage in a minimum of 10 days professional development pro rata per year, recognising that researchers will pursue careers across a wide range of employment sectors. | a) Create a toolkit to identify activities constituting professional development to aid in researchers better recognising professional development. b) Doctoral School to develop means of researchers accessing training via asynchronous options. c) Offering select training sessions as part of the Academic Development Programme as online e-learning sessions to improve upon accessibility. d) Utilise established engagement groups to understand any potential concerns with the expectations of development and reviewing research allocations in the workloading tariffs, which will be reintroduced. e) Support the development of research staff skills and activity. This includes training schemes, support mechanisms, and funding schemes to pump-prime specific activity, including local discretionary funding and central competitive and strategically focused investment. This will embed greater KE capability and commercial awareness to leverage opportunities. | No | 2023-12-01 | a) Head of Organisational Development and People Change and Policy Manager b) Director of Doctoral School c)Researcher Development Officer d) People Change and Policy Manager e) College Directors of Research | i) In CEDARS 2025, increase the number of respondents engaging in 10 days professional development from 6% (CEDARS 2021) to 15%. ii) In PRES 2021, 79.1% of UoL PhD students were satisfied with the level of professional developent at Lincoln. Increase this figure to 85% in PRES 2023. iii) Engage a minimum of 30 PGRs with new asychronous programme as part of the Researcher Development Programme. iv) Increase research staff/ECR engagement with the Academic Development Programme and specific ECR focused training workshops as part of Reseach First by 30% by the end of the 23/24 academic year.
PCDI6 | Monitor, and report on, the engagement of researchers and their managers with professional development activities. | a) Improve access to effective development opportunities and review the availability and advertising of secondment and acting up opportunities across the University. | Yes | 2023-12-01 | a) People Operational Services Manager | i) In CEDARS 2021, 58% of researchers agreed that their line manager encourages them to engage in personal and career development activities. Increase this score to 65% by CEDARS 2025. ii) In CEDARS 2021, only 13% of researchers agreed that their manager/supervisor encourages them to consdier a wide range of future career options within and beyond academia. Increase this figure to at least 30% in CEDARS 2025.
PCDM3 | Managers allocate a minimum of 10 days pro rata per year, for their researchers to engage with professional development, supporting researchers to balance the delivery of their research and their own professional development. | See PDCI1
PCDR1 | Researchers take ownership of their career, identifying opportunities to work towards career goals, including engaging in a minimum of 10 days professional development pro rata per year. | a) Promote Doctoral Grants scheme to fixed-term PDRAs. | Yes | 2023-09-01 | Researcher Development Officer | i) Offer 12 Doctoral School grants to pairs of PGRs/fixed-term PDRAs by the end of the 22/23 academic year. At least 4 grants to go to a PGR/PDRA pairing.
Career development reviews
The aims of these obligations are to ensure researchers and their managers are engaging in productive career development reviews.
PCDI2 | Provide training, structured support, and time for managers to engage in meaningful career development reviews with their researchers. | a) Based on the results of the Staff Survey 2022, more work needs to be done to ensure that research appraisals are useful and valuable. There also needs to be more in-depth training to ensure managers/appraisers have the confidence to ensure these conversations are performance driven. Appraisal training will be enhanced to ensure there is a performance-driven culture. | No | 2023-07-01 | a) Head of Organisational Development | i) AAPR completion rates for 2022/23 were 84% across the University, however researchers only had a 58% completion rate. Aim for researchers to have an AAPR completion rate of 68% in 24/25. ii) Explore career development as a topic of discussion at Concordat Consultation Group and research network meetings to seek feedback on what additional career development and support would be beneficial to researchers.
PCDI6 | Monitor, and report on, the engagement of researchers and their managers with researcher career development reviews. | See PCDi2
PCDM1 | Managers engage in regular career development discussions with their researchers, including holding a career development review at least annually. | a) Managers of researchers to have up-to-date information to share with staff regarding professional development and be supportive of career aspirations, particular focus to be given to BAME staff in line with REC action plan. | Yes | 2024-03-01 | a) Head of Organisational Development and Director of Inclusive Practice | i) AAPR completion rates for 2022/23 were 84% across the University, however researchers only had a 58% completion rate. Aim for researchers to have an AAPR completion rate of 68% in 24/25. ii) CEDARS 2021: 58% of respondents agreed that their manager encouraged them to engage in personal and career development activities. Increase this to 65% in CEDARS 2025. iii) Ensure career development reviews are deemed useful by researchers. In CEDARS 2021, of those who had regular career development reviews, only 25% of respondents found them useful. Aim for an increase in this score. iv) REC 2021: 54.4% of BAME respondents reported that their line managers made time for their development in comparison to 74.0% of White staff. To improve equity between BAME and White respondents around time being made to discuss development with responses of at least 75%. | a) There needs to be a particular focus on BAME staff following the REC 2021 result as follows: 54.4% of BAME respondents reported that their line managers made time for their development in comparison to 74.0% of White staff.
PCDR4 | Researchers positively engage in career development reviews with their managers. | a) Appraiser training is being redesigned in 2023, and there will be an increased focus on ensuring the appraisee gets the most out of the conversation and is engaged with it. AAPR completion data will continue to be monitored and submitted to PPCC. | No | 2023-07-01 | a) Head of Organisational Development | i) AAPR completion rates for 2022/23 were 84% across the University, however researchers only had a 58% completion rate. Aim for researchers to have an AAPR completion rate of 68% in 24/25. ii) Ensure career development reviews are deemed useful by researchers. In CEDARS 2021, of those who had regular career development reviews, only 25% of respondents found them useful. Aim for an increase in this score to 35% in CEDARS 2025.
Career development support and planning
The aims of these obligations are to promote researchers' career development planning through tailored support and gathering evidence of professional experience.
PCDI3 | Ensure that researchers have access to professional advice on career management, across a breadth of careers. | a) Develop careers provision for PGRs and ECRs via the Doctoral School through specific programmes including the UoL Life Beyond the PhD, by focusing on an array of lucrative careers in industry, e.g. Agritech. b) Provide PGRs with entrepreneurial skills in order to support future commericalisation of research. This will include student enterprise as an integral part of PGR induction. c) Promote the EGI Pipeline menoring scheme via the new Research staff induction. | No | 2025-08-01 | a, b) Director of the Doctoral School c) EGI/Director of Inclusive Practice | i) Aim for a minimum of 15 PGR students to complete the PGR Enterprise Bootcamp planned for Spring 2023. ii) CEDARS 2023, aim for 20% of UoL respondents agreeing that their supervisor/manager encourages them to consider a wide range of future career options beyong academia. iii) In CEDARS 2023, aim for 50% of UoL respondents to be aware of support UoL provides for career and professional development. iv) Aim for a minimum of 30 PGRs to participate in Life Beyond the PhD sessions. v) Increase research staff involvement in EGI Pieline mentoring scheme by 5% by 2024.
PCDR3 | Researchers maintain an up-to-date professional career development plan and build a portfolio of evidence demonstrating their experience, that can be used to support job applications. | a) Review how to incorporate research identity and research specific leadership skills within the researcher development programme. | Yes | 2025-08-01 | a) Researcher Development Officer and Head of Organisational Development | i) In CEDARS 2021 results, 24% of respondents had a clear development plan. Increase this figure in CEDARS 2025 to 30%. ii) In CEDARS 2021 results, 63% of respondents agreed that they had a clear career development plan. Increase this figure to 70% in CEDARS 2025.
Research identity and leadership
The aims of these obligations are to provide researchers with opportunity to progress in their careers by developing their research identity and leadership capabilities.
PCDI4 | Provide researchers with opportunities, and time, to develop their research identity and broader leadership skills. | a) Increase opportunities for leadership training by provide specific ECR-focused research leadership training, with a view to increase confidence as a leader and engaging with colleagues and considering own role at a strategic level. b) Provide research impact and KE training as a mandatory element of research staff/PGR induction. c) Promote any research specific training run by R&E and borader leadership training in HR Line and via the new Academic Development Programme website and comms to ensure there is a joined-up approach to coordinating and promoting training opportunities across the University, resulting in increased engagement levels. | No | 2023-04-01 | a and b) Researcher Development Officer c) Impact Development Officer and People Change and Policy Manager | i) Aim for a minimum of 16 partipants in research leadership training. ii) In CEDARS 2023, aim for 45% of respondents to have obtained leadership training. iii) Participation levels in research specific training run by R&E increase by 10% by 2024. iv) Facilitate an increase of researchers in all leadership training offered by the University of Lincoln including: ILM, Academic Apprenticeship, Inspire, and Aurora. In these programmes 216 employees have participated in last five years. We will aim to increase the number of participants by 10% in 2025.
PCDM4 | Managers identify opportunities, and allow time (in addition to the 10 days professional development allowance), for their researchers to develop their research identity and broader leadership skills, and provide appropriate credit and recognition for their endeavours. | a) Managers to encourage researchers to apply for leadership training taking place in March 2023, and support applications with a letter of recommendation. | Yes | 2024-08-01 | a) Researcher Development Officer | i) Aim for a minimum of 16 partipants in research leadership training.
PCDM5 | Managers engage in leadership and management training to enhance their personal effectiveness, and to promote a positive attitude to professional development. | a) Continue to engage with leadership training to improve their skills as research leaders. Appropriate training may include, but is not limited to, management training (ILM and Chartered Manager Degree Apprenticeship), the Academic Professional Apprenticeship and leadership programmes for women (Aurora through Advanced HE) and BAME employees (Inspire). | Yes | 2024-07-01 | a) Head of Organisational Development | i) Facilitate an increase of participants in all leadership training offered by the University of Lincoln including: ILM, Academic Apprenticeship, Inspire, and Aurora. In these programmes 216 employees have participated in last five years. We will aim to increase the number of participants who are researchers by 10% by 2025.
PCDR5 | Researchers to seek out, and engage with, opportunities to develop their research identity and broader leadership skills | a) Continue to develop an effective Academic Research Development programme and advertise via a new ADeP website to encourage engagement and participation. b) Doctoral School to provide 12 research grants to pairs of doctoral students or doctoral students/PDRAs to encourge cross-collaboration research as well as leadership skills. Doctoral student/PDRA partnership to include elements of mentorship. c) Following formal inclusion as an institution in the British Academy’s Early Career Research Network for the Midlands, promote ECR events on Sustainability, Working with Industry and building research culture through writing communities | No |  | a-c) Researcher Development Officer | i) Aim to increase research-only staff engagement with the Academic Development Programme by 30% in the 23/24 academic year. ii) Award 12 research grants to pairs of sucessful doctoral students/doctoral student and PDRAs, and measure impact of the research project through impact statements post-award (to be submitted in September 2023). Share sucess stories through Doctoral School and R&E newsletters to both increase research staff/PGR visibility, and to encourage uptake from researchers for future calls. iii) ECR attendance at BA training events. Evaluate experiences of attending training through follow-on discussions to share experiences and best pracice, and staff training feedback forms.
Diverse careers
The aims of these obligations are to recognise, value and prepare researchers for the wide range of career options available to them within and beyond research.
PCDI5 | Recognise that moving between, and working across, employment sectors can bring benefits to research and researchers, and support opportunities for researchers to experience this. | a) Consider providing opportunities to develop outside of academia through partnership working and secondments. Pilot new inward and outward secondment scheme as part of the HEIF strategy on impact accelerator, particularly seeking opportunities for industrial secondments with public, private and third sector. This will be used to facilitate partnership development, commercial awareness, impact and to facilitate knowledge exchange between UoL and Industry. b) Review the use of collecting information from new starter questionnaires and exit surveys regarding the next role for researchers to understand career stages of researchers. Review what information could be collected at the onboarding stage of recruitment. Both would help inform future support for researchers. c) Doctoral School to provide cross-collaboration opportunities for PGRs and Fixed-term PDRAs. d) Develop tools to support managers with Talent and Succession Planning. e) Launch a new centrally-funded sabbatical scheme exclusively for staff on research profiles to prioritise research development and maximise the potential of quality-related funding. The scheme will run from academic year 2023/24 and provide the prospect of up to 40 individuals being granted sabbatical periods in any given year. f) Increase school discretionary budgets with an emphasis on supporting ECRs and those with high research potential to attend international conferences to help build networks and increase international collaboration. | a-c) Yes d-f) No | 2023-08-01 | a) Deputy Director of PPC, Head of Research and Industrial Partnerships b) People Change and Policy Manager c) Director of the Doctoral School d) Head of Organisational Development e) College Directors of Research f) DVC of Research and Innovation | i) Impact Accelaterator fund for both experienced and early-stage impact development. ii) Allocation of twelve Doctoral School grants for cross-collaborative research by end of July 2023. iii) Target of 75% take-up for the sabbatical scheme in 2023/24. iv) Target of 4 researchers to participate in the secondment scheme each year.
PCDM2 | Managers support researchers in exploring and preparing for a diversity of careers, for example, through the use of mentors and careers professionals, training, and secondments. | See PCDI1 plus: a) Following formal inclusion as an institution in the British Academy’s Early Career Research Network for the Midlands. A number of experienced resarch staff are serving on their key committees and working groups, and offering mentorship to ECRs. | Yes | 2024-08-01 | a) College Directors of Research | i) Delivery of two British Academy ECR network multidisciplinary events by April 2023.
PCDR2 | Researchers explore and prepare for a range of employment options across different sectors, such as by making use of mentors, careers professionals, training and secondments. | a) Encourage PGRs and ECRS to take advantage of schemes such as the Associate Fellowship HEA provided by LALT. b) Support researchers with their career plans and assist them with career diversification. | No | 2024-08-01 | a) Dean of LALT and Researcher Development Officer b) Heads of School | i) Increase awareness and understanding of the Concordat for the advancement of knowledge exchange in higher education from 15.1% (CEDARS 2021) to 30% in CEDARS 2025. ii) Aim for a minimum of 15 PGR students to complete the PGR Enterprise Bootcamp planned for Spring 2023.
PCDR6 | Researchers consider opportunities to develop their awareness and experience of the wider research system through, for example, knowledge exchange, policy development, public engagement and commercialisation. | a) ECRs to attend training sessions as part of Research First, such as bid writing and research impact. b) Promote applications to the UoL Impact Accelerator fund. c) Encourage engagement with the principles and UoL action plan of the KE Concordat via research staff induction. | No | 2024-08-01 | a) Research Development Manager b) Industrial Partnerships Manager c) Researcher Development Officer | i) Increase awareness and understanding of the Concordat for the advancement of knowledge exchange in higher education from 15.1% (CEDARS 2021) to 30% in CEDARS 2025. ii) Measure increased opportunities for PGRs to be involved in the wider research community via PRES 2023. Increase score from 47.9% in PRES 2022 to 50% in PRES 2023.
* The Researcher Development Concordat defines researchers as individuals whose primary responsibility is to conduct research and who are employed specifically for this purpose by a higher education institution or research institute. The primary audience is research staff, e.g. postdoctoral researchers, research fellows, research assistants. The Researcher Development Concordat encourages institutions to include other groups who actively engage in research as beneficiaries of their Concordat action plan. These could be postgraduate researchers; staff on teaching and research, or teaching contracts; clinicians; professional support staff; technicians.
Further hyperlinks and supplementary information (more rows can be added) |  |  |  |  | Abbreviations and glossary (more rows can be added)
1 | Patricia C. Jackman, Rebecca Sanderson & Lisa Jacobs (2021) Developing inductions to support mental health and wellbeing in doctoral researchers: findings from a qualitative co-design study with doctoral researchers and university stakeholders, European Journal of Higher Education, DOI: 10.1080/21568235.2021.1992293 |  |  |  | AAPR | Annual Academic Planning Review
2 | One Community Values: https://www.lincoln.ac.uk/abouttheuniversity/onecommunity/ |  |  |  | AWM | Academic Workload Model
3 | University of Lincoln Strategic Plan 2022-27: https://www.lincoln.ac.uk/media/responsive2017/abouttheuniversity/managementandstrategy/UOL-Strategic-Plan-2022-2027.pdf |  |  |  | BAME | Black, Asian and Minority Ethnic
4 |  |  |  |  | CEDARS | Culture, Employment and Development in Academic Research Survey
5 |  |  |  |  | CROS | Careers in Research Online Survey
6 |  |  |  |  | DORA | San Francisco Declaration on Research Assessment
7 |  |  |  |  | EAG | Equality Advisory Group
8 |  |  |  |  | ECR | Early Career Researcher
9 |  |  |  |  | EDI | Equality, Diversity and Inclusion
10 |  |  |  |  | EGI | Eleanor Glanville Institute
[5 empty] | EIA | Equality Impact Assessments
11 |  |  |  |  | FTC | Fixed term contracts
12 |  |  |  |  | GTA | Graduate Teaching Assistant
[5 empty] | HEIF | Higher Education Innovation Funding
13 |  |  |  |  | HoS | Head of School
[5 empty] | ILM | Institute of Leadership and Management
14 |  |  |  |  | IRP | Individual Research Plan
15 |  |  |  |  | ISPP | Individual Scholarly and Professional Practice Plan
16 |  |  |  |  | JEDI | Joint Equality, Diversity and Inclusion partnership
17 |  |  |  |  | LALT | Lincoln Academy of Learning & Teaching
18 |  |  |  |  | LEAS | Lincoln Ethics Application System
19 |  |  |  |  | LHERI | Lincoln Higher Education Research Institute
20 |  |  |  |  | LIAS | Lincoln Institute for Advanced Studies
[5 empty] | PEARL – | Public Engagement for All with Research at Lincoln
[5 empty] | PG | Post-graduate student
[5 empty] | PGR | Post-Graduate Researcher
[5 empty] | PPC | Department of People, Performance and Culture
[5 empty] | PPCC | People, Performance and Culture Committee
[5 empty] | PRES | Postgraduate Research Experience Survey
[5 empty] | QR | Quality Related
[5 empty] | REC | Race Equality Charter
[5 empty] | R&E | Research and Enterprise
[5 empty] | RKE | Research and Knowledge Exchange
[5 empty] | RKEC | Research and Knowledge Exchange Committee
[5 empty] | SLT | Senior Leadership Team
[5 empty] | SME | Small and medium-sized enterprises
[5 empty] | T&R | Teaching and Research academic role profile
[5 empty] | TSPP | Teaching, Scholarly and Professional Practice academic role profile
[5 empty] | UCEA | Universities and Colleges Employers Association
[5 empty] | UKRIO | UK Research Integrity Office
[5 empty] | UoL | University of Lincoln
[5 empty] | UREC | University Research Ethics Committee